# Team Assignment 3 – Network Diagram

**MET AD 642: Group 2 - Team D**

**Ashley Avona, Samantha Germano , Lailumah Nadeem**

**Activities for Scheduling**

| **ID** | **Task Name** | **Duration (days)** |
| --- | --- | --- |
| A | Internal Stakeholder Requirements Summary | 3 |
| B | External Stakeholder Feedback Report | 3 |
| C | Existing Website Audit | 2 |
| D | Information Gap Analysis | 2 |
| E | Final Requirements Document | 2 |
| F | Brand Design Kit | 4 |
| G | Venue Photography | 3 |
| H | Service Provider Info Packet | 2 |
| I | Updated Website Content | 3 |
| J | Website Architecture Blueprint | 4 |
| K | Front-End Interface | 5 |
| L | Back-End Functionality | 5 |
| M | Content & Media Integration | 1 |
| N | Internal Design Review | 1 |
| O | Internal Quality Assurance | 2 |
| P | Stakeholder Testing | 2 |
| Q | Bug Fixes | 2 |
| R | Final Review & Approval | 1 |
| S | Public Launch | 1 |
| T | Post-Launch Evaluation | 4 |

**Dependencies**

| **ID** | **Task Name** | **Depends On** |
| --- | --- | --- |
| A | Internal Stakeholder Requirements Summary | — |
| B | External Stakeholder Feedback Report | — |
| C | Existing Website Audit | — |
| D | Information Gap Analysis | A, B, C |
| E | Final Requirements Document | D |
| F | Brand Design Kit | E |
| G | Venue Photography | E |
| H | Service Provider Info Packet | E |
| I | Updated Website Content | G, H |
| J | Website Architecture Blueprint | F |
| K | Front-End Interface | J |
| L | Back-End Functionality | J |
| M | Content & Media Integration | I, K, L |
| N | Internal Design Review | M |
| O | Internal Quality Assurance | N |
| P | Stakeholder Testing | O |
| Q | Bug Fixes | P |
| R | Final Review & Approval | Q |
| S | Public Launch | R |
| T | Post-Launch Evaluation | S |

**Critical Path :**

A + B + C → D → E → F → J → K → M → N → O → P → Q → R → S → T  
(3+3+2) + 2 + 2 + 4 + 4 + 5 + 2 + 1 + 2 + 2 + 2 + 1 + 1 + 4 = **39 days**

**Network Schedule Table**

| **ID** | **Task Name** | **Duration** | **Predecessors** |
| --- | --- | --- | --- |
| A | Internal Stakeholder Requirements Summary | 3 | — |
| B | External Stakeholder Feedback Report | 3 | — |
| C | Existing Website Audit | 2 | — |
| D | Information Gap Analysis | 2 | A, B, C |
| E | Final Requirements Document | 2 | D |
| F | Brand Design Kit | 4 | E |
| G | Venue Photography | 3 | E |
| H | Service Provider Info Packet | 2 | E |
| I | Updated Website Content | 3 | G, H |
| J | Website Architecture Blueprint | 4 | F |
| K | Front-End Interface | 5 | J |
| L | Back-End Functionality | 5 | J |
| M | Content & Media Integration | 2 | I, K, L |
| N | Internal Design Review | 1 | M |
| O | Internal Quality Assurance | 2 | N |
| P | Stakeholder Testing | 2 | O |
| Q | Bug Fixes | 2 | P |
| R | Final Review & Approval | 1 | Q |
| S | Public Launch | 1 | R |
| T | Post-Launch Evaluation | 4 | S |

**Mapping Milestones to Network Activities:**

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone Phase** | **Milestone Description** | **Corresponding Activities (from WBS/Network)** | **Date Range** |
| **Phase #1: Analysis, Outreach & Approval** | Kickoff, website audit, photography, internal info gathering | **A, B, C, G, H** – Internal & External requirements, Existing website audit, Venue photography, Provider info | Aug 15 – Sep 1, 2025 |
|  | Information Gap Analysis & Final Requirements | **D, E** – Analysis of gaps and final requirement documentation | Aug 20 – Sep 5, 2025 |
| **Phase #2: Design & Development** | Brand Design Kit & Architecture Design Plan | **F, J** – Brand Design Kit, Website Architecture Blueprint | Sep 5 – Sep 27, 2025 |
|  | Front-End and Back-End Development | **K, L** – Interface and Functionality | Sep 30 – Nov 10, 2025 |
| **Testing** | Internal QA, Stakeholder Testing, Bug Fixes | **O, P, Q** – QA, Stakeholder Testing, Fixes | Nov 11 – Dec 5, 2025 |
| **Launch** | Final Review and Public Launch | **R, S** – Final Approval, Public Launch | Dec 10 – Dec 30, 2025 |
| **Post-Launch** | Post-launch Evaluation & Performance | **T** – Post-Launch Evaluation | Jan 2 – Jan 10, 2026 |

A line of black squares

AI-generated content may be incorrect.

**Hand Drawn Network diagram** A graph on a notebook

AI-generated content may be incorrect.

A paper with writing on it

AI-generated content may be incorrect.