## Sheet1
Cost Estimate
Project Name: Improved EECP Website Launch | Date: |  | 2025-06-03
Team D: Ashley Avona, Samantha Germano, Lailumah Nadeem
WBS Categories | Internal Labor Hours | Number of People | Rate/hour | Internal Costs Total | External Labor Hours | Number of People | Rate/hour | External Costs Total | Total Cost | Notes
1 Analysis, Outreach, and Approval
1.1 Internal Stakeholder Requirements | 1 | 3 | 105 | 315 | - | - | - | - | 315 | Project Managers
1.2 External Stakeholder Feedback Report | - | - | - | - | 0.16667 | 10 | 0 | 0 | 0 | No compensation which will be communicated to external partners who are taking a voluntary survey
1.3 Existing Website Audit | 3 | 3 | 105 | 945 | - | - | - | - | 945 | Project Managers
1.4 Information Gap Analysis | 1 | 3 | 105 | 315 | - | - | - | - | 315 | Project Managers
1.5 Service Provider Interviews Summary | 0.16667 | 6 | 180 | 180 | - | - | - | - | 180 | Feedback survey to Service Providers and Venue Managers. Estimated to be about ten minutes
1.6 External Client Feedback Report | - | - | - | - | 0.16667 | 10 | 0 | 0 | 10.1667 | No compensation which will be communicated to external partners who are taking a voluntary survey
1.7 Venue Data Collection |  |  |  |  | - |  | - |  |  | Cost broken down into sections
1.7.1 Most Requested Venues Report | 0.5 | 1 | 35 | 17.5 | - | - | - | - | 17.5
1.7.2 Venue Capacity Matrix | 1 | 1 | 35 | 35 | - | - | - | - | 35
1.7.3 Setup Configuration Summary | 1 | 1 | 35 | 35 | - | - | - | - | 35
1.7.4 Availability Calendar | 0.5 | 1 | 35 | 17.5 | - | - | - | - | 17.5 | Dates when booking venues become available (ex: availability is released in January for events in the summer)
1.8 Final Requirements Document | 1 | 3 | 105 | 315 | - | - | - | - | 315
1.9 Sponsor Approval Form | 0.16667 | 1 | 35 | 5.8333 | - | - | - | - | 5.8333
2. Content and Media Preparation
2.1 Brand Design Kit | [9 empty] | Cost broken down into sections
2.1.1 Color Scheme | 1.5 | 1 | 35 | 52.5 | - | - | - | - | 52.5 | Completed by marketing representative and formulated using Northeastern's premade brand guidelines
2.1.2 Font Set | 1.5 | 1 | 35 | 52.5 | - | - | - | - | 52.5 | Completed by marketing representative and formulated using Northeastern's premade brand guidelines
2.1.3 Logo Assets | 2 | 1 | 35 | 70 | - | - | - | - | 70 | Completed by marketing representative and formulated using Northeastern's premade brand guidelines
2.2 Venue Photography | - | - | - | - | 12 | 1 | 150 | 1800 | 1800
2.2.1 Photographer Scheduling | 2 | 1 | 35 | 70 | - | - | - | - | 70 | Research, inquiry, contracting, scheduling
2.2.2 Venue Photo Gallery | 2 | 1 | 35 | 70 | - | - | - | - | 70 | Gallery of venues with common setups
2.3 Service Provider Information Packets | 0.5 | 6 | 30 | 90 | - | - | - | - | 90 | Already made, just a review and upload
2.4 Updated Website Content | [9 empty] | Cost broken down into sections
2.4.1 Service Descriptions | 4 | 1 | 35 | 140 | - | - | - | - | 140
2.4.2 Inquiry Submission Instructions | 0.5 | 1 | 35 | 17.5 | - | - | - | - | 17.5
2.5 Branding and Compliance Review Submission | 0.16667 | 1 | 35 | 5.8333 | - | - | - | - | 5.8333
3. Website Design and Development
3.1 Website Architecture Blueprint | 2 | 3 | 35 | 210 | - | - | - | - | 210 | Project Managers
3.2 Front-End Interface | [9 empty] | Cost broken down into sections
3.2.1 Navigation System | 8 | 1 | 35 | 280 | - | - | - | - | 280
3.2.2 Home Page | 8 | 1 | 35 | 280 | - | - | - | - | 280
3.2.3 Venue Details Page | 8 | 1 | 35 | 280 | - | - | - | - | 280
3.2.4 Inquiry Form Page | 1 | 1 | 35 | 35 | - | - | - | - | 35
3.3 Back-End Functionality | [9 empty] | Cost broken down into sections
3.3.1 Submission Form Integration | 1 | 1 | 35 | 35 | - | - | - | - | 35
3.3.2 CMS Implementation | 8 | 2 | 35 | 560 | - | - | - | - | 560
3.4 Content and Media Integration | 8 | 2 | 35 | 560 | - | - | - | - | 560 | IT and Marketing
3.5 Internal Design Review (IT and Marketing) | 2 | 2 | 35 | 140 | - | - | - | - | 140 | IT and Marketing
4. Testing and Launch
4.1 Internal Quality Assurance Report | 8 | 1 | 35 | 280 | - | - | - | - | 280
4.2 Stakeholder Testing Summary | 1 | 6 | 30 | 180 | 1 | 10 | 0 | 0 | 180 | No compensation for external reviewers which will be communicated to external partners who are voluntarily reviewing website
4.3 Bug and Issue Log | 3 | 2 | 35 | 210 | - | - | - | - | 210
4.4 Final Review and Approval | 4 | 3 | 35 | 420 | - | - | - | - | 420 | All service providers and venue managers confirm their venues are depicted accurately
4.5 Public Website Launch | 1 | 1 | 35 | 35 | - | - | - | - | 35
5. Post-Launch Evaluation
5.1 Website Performance Report | [9 empty] | Cost broken down into sections
5.1.1 Site Traffic Analytics | 2 | 1 | 35 | 70 | - | - | - | - | 70
5.1.2 Page Load Time Report | 1 | 1 | 35 | 35 | - | - | - | - | 35
5.1.3 Mobile Responsiveness Test | 0.5 | 1 | 35 | 17.5 | - | - | - | - | 17.5
5.1.4 Core Web Vitals Score | 0.5 | 1 | 35 | 17.5 | - | - | - | - | 17.5
5.2 User Satisfaction Survey Results | - | - | - | - | 0.16667 | 10 | 0 | 0 | 0 | No compensation which will be communicated to external partners who are taking a voluntary survey
5.3 Final Project Report | 8 | 3 | 35 | 840 |  | - |  |  | 840 | Project Managers
5.4 Lessons Learned Summary | 8 | 3 | 35 | 840 | - | - | - | - | 840 | Project Managers
Subtotal | 106.5 |  |  | 8074.1667 | 13.5 |  |  | 1800 | 9884.3333
Reserve | [8 empty] | 115.6667
Total | [8 empty] | 10000
IMPORTANT ASSUMPTIONS
1) Budget in USD
2) A full day is assumed to be eight hours
3) PM team consists of three leads making $35 an hour
4) Campus service providers and event managers consulting on the project make $30 an hour. Each department will provide one representative (total of six members). Not all members of the team will be used for each part of the project.
5) ITS and Marketing department consist of one person each at a cost of $35 per hour. Not all members of the team will be used for every part of the project.
6) All University employees are on a salary basis. The hours contributed to this project will be logged and taken from the project budget instead of the normal salary budgets as part of the deal to have these representatives on the team.
7) All hourly rates were estimated based on average University salaries for service providers and event managers.
8) A photographer will be the only external vendors compensated monetarily.
9) Surveys and website reviews by external clients will be voluntary participation without compensation. This will be clearly communicated to external partners.
10) Ten external clients will participate in the external review. Surveys are estimated to take ten minutes and reviews are estimated to take one hour to complete.