## Threats
Risk Register
Number | Event Name | Probability | Impact
1 | Inquiries lost during form transition | 4 | 4.5
2 | Internal reviews miss key information gaps | 3 | 4.5
3 | Limited budget prevents full implementation | 2.5 | 5
4 | IT Team unable to implement desired features | 3 | 4
5 | Website form bugs post-launch | 3 | 3
6 | Delays in receiving venue photos | 2 | 3
7 | Branding review delay from University Marketing | 3 | 3.5
8 | Low user satisfaction post-launch | 2.5 | 4
9 | Stakeholder testing reveals major flaws | 3.5 | 3.5
10 | Service providers miss deadlines | 2.5 | 3
Probability | Key
1 | Rare
2 | Unlikely
3 | Possible
4 | Likely
5 | Certain
Impact
1 | Trivial
2 | Mild
3 | Significant
4 | Major
5 | Catastrophic